## Sheet1
Sprint Backlog | Description | effort (person hours) | responsible | status | status notes
1.1 | Create sprint backlog | 1 | Beki | Completed
1.2 | Become familiar with Android SDK | 2 | Neill | Completed
1.3 | Download phone drivers and Android SDK | 1 | Ross | Completed
1.4 | Download and set up Git Hub | 2 | Beki | Completed
1.5 | Download and install IDE | 1 | Ross | Completed
1.6 | Agree programming standards | 1 | Neill | Completed
1.7 | Agree team charter | 1 | Beki | Completed
1.8 | Prototype UI | 1 | Neill | Completed
1.9 | Research what type of information is related with shares and search for a suitable source of share information | 1 | Ross | Completed
1.1o | Construct GUI to display information and internet with user | 6 | Beki | Completed
1.11 | Testing phone compatibility | 1 | Jeff | Completed
2.1 | As a user I want to see how much my total portfolio is worth
2.2 | Program a method that retrieves the price of shares | 2 | Jeff | Completed
2.3 | Construct method to calculate the retrieved shares total | 4 | Jeff | Completed
2.4 | Display portfolio total worth in £ | 2 | Neill | Completed
2.5 | Costruct a method to calculate the total value of each set of shares | 4 | Jeff | Completed
3.1 | As a user I would like an estimate of how much each set of shares is worth
3.2 | Program a method that retrieves the price of shares | 2 | Ross | Completed
3.3 | Costruct a method to calculate the total value of each set of shares | 4 | Ross | Completed
3.4 | Display total worth of each set of shares in £ | 2 | Ross | Completed