## Sheet1
Sprint Backlog | Description | effort (person hours) | responsible | status | status notes | 2011-11-07 | 2011-11-08 | 2011-11-09 | 2011-11-10 | 2011-11-11 | 2011-11-14 | 2011-11-15 | 2011-11-16 | 2011-11-17
| Create sprint backlog | 1 | Beki | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Write acceptance tests | 1 | Beki | Completed |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| New icons | 1 | Neill | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add Bowleven PLC Oil | 1 | Neill | Completed |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Black testing box | 1 | Beki | Completed |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create 2 new tabs for the 2 new features | 2 | Neill | Completed |  | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Report a drop of 20% | 1 | Neill | Completed |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Report a rise of 20% | 1 | Neill | Completed |  | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 0 | 0
| Calculate share drop percentage | 2 | Ross | Completed |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Calculate share rise percentage | 2 | Ross | Completed |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement colours system red = plummet green = rocket | 1 | Neill | Completed |  | 1 | 1 | 1 | 2 | 3 | 3 | 3 | 2 | 0
| Work out the set with the highest % chance and the lowest % change | 3 | Beki | Completed |  | 3 | 3 | 4 | 3 | 3 | 2 | 1 | 0 | 0
| Display the best and worst performing shares | 1 | Beki | Completed |  | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 0
| Get the previous values to round up | 1 | Beki | Completed |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Create method to display the data | 1 | Jeff | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create method to format the data | 1 | Jeff | Completed |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Create method to calculate the percent change i.e "is share on run" | 2 | Jeff | Completed |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create method to get the volume of each share set | 1 | Jeff | Completed |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| create method to get the current value of each share set | 1 | Jeff | Completed |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Construct a method that displays the rise and fall of shares | 1 | Ross | Completed |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Display the total rise and fall of each set of shares | 1 | Jeff | Completed |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Calculate the change in each share at the end of the day based on its value at the start of the day | 3 | Ross | Completed |  | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0
| Total hours remaining: | 30 |  |  |  | 26 | 21 | 19 | 16 | 16 | 12 | 8 | 3 | 0