## Sheet1
Sprint Backlog | Description | effort (person hours) | responsible | status | status notes | 2011-10-10 | 2011-10-11 | 2011-10-12 | 2011-10-13 | 2011-10-14 | 2011-10-17 | 2011-10-18 | 2011-10-19 | 2011-10-20 | 2011-10-21
1.1 | Create sprint backlog | 1 | Beki | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Become familiar with Android SDK | 2 | Neill | Completed |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0
1.3 | Download phone drivers and Android SDK | 1 | Ross | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Download and set up Git Hub | 2 | Beki | Completed |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 | Download and install IDE | 1 | Ross | Completed |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 | Agree programming standards | 1 | Neill | Completed |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
1.7 | Agree team charter | 1 | Beki | Completed |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0
1.8 | Prototype UI | 1 | Neill | Completed |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
1.9 | Research what type of information is related with shares and search for a suitable source of share information | 1 | Ross | Completed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1o | Construct GUI to display information and internet with user | 6 | Beki | Completed |  | 6 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0
1.11 | Testing phone compatibility | 1 | Jeff | Completed |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2.1 | As a user I want to see how much my total portfolio is worth
2.2 | Program a method that retrieves the price of shares | 2 | Jeff | Completed |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
2.3 | Construct method to calculate the retrieved shares total | 4 | Jeff | Completed |  | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0
2.4 | Display portfolio total worth in £ | 2 | Neill | Completed |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Costruct a method to calculate the total value of each set of shares | 4 | Jeff | Completed |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | As a user I would like an estimate of how much each set of shares is worth
3.2 | Program a method that retrieves the price of shares | 2 | Ross | Completed |  | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 0 | 0
3.3 | Costruct a method to calculate the total value of each set of shares | 4 | Ross | Completed |  | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0
3.4 | Display total worth of each set of shares in £ | 2 | Ross | Completed |  | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Total hours remaining: | 38 |  |  |  | 33 | 29 | 25 | 19 | 14 | 13 | 9 | 8 | 4 | 0